## Slide 1: ACLAD Status 9/9/2024
Maintenance
  10 wells operational on generators, 7 wells sheared, 2 wells need various repairs (No Change)
  Installed 9 Generators
    Large propane tanks installed
    Thank you to the Generator Team (turn on/off)
  Repaired multiple drain system breaks
    Average 1-2 per week
    Some wells turned off for repairs
Kelvin Canyon
  J.Lowe donated 2 - 600 gal tanks for clarifier and to provide system input pressure into WW 15
  Need volunteer to help plumbing into WW 15
Surface Drainage
  Met with Hout and Malcolm on“Winterization Plan”
    Grading of Altamira Canyon fissures started
  High priority projects:
    Narcissa atPBRC
    Upper Narcissa to Ginger Root
    Narcissa/Cinnamon
    Figtree cul de sac
    Vanderlip Dr.
View looking
Down WW 4
Other Activities
  Bore hole drilling near WW9 to assess Deep Water Well feasibility
  Need volunteer to help with Cal OES fuel reimbursement application
  5-11 wells need solar power
    24/7 wells need ~36 panels and ~45 Kah Batteries
    Looking into DC pumps with daytime only operation
    Need volunteer to coordinate for ACLAD
Detailed well status follows

## Slide 2: Individual well status: 10/14/24 Total Last Week 74,504 + WW 10
WW | Location | GPD* | Comments
1 | Narcissa/Ginger Root | 11,754 | Generator Installed
2 | Lower Narcissa |  | Sheared, pump stuck in casing, Will look into alternative pumps
3 | Figtree | 640 | Generator Installed
4 | Lower Figtree |  | Sheared
6 | Clove Tree | 4,392 | Generator Installed, Need to remove plumbing from new well
7 | Mid Narcissa |  | Sheared
8 | Mid Sweetbay |  | Sheared
9 | Beach School |  | No Power
10 | Figtree Cul de sac | ??? | Generator Installed, Pumping water, Needs new meter
11 | Bean Field |  | No Power
12 | Upper Ginger Root | 16,200 | Generator Installed, Meter replaced

## Slide 3: Individual well status 10/14/24
WW | Location | GPD* | Comments
13 | King/Sweetbay | 15,151 | Generator Installed
15 | Vanderlip/Narcissa | 12,000 | Generator Installed
16 | Petak/Sweetbay | 758 | Generator Installed Sheared, Water level 26’. Installed surface pump
17 | Thyme | 5,832 | Working on sewer generator, Replaced pump
18 | Olmsted |  | No Power
19 | Beach School |  | No Power
20 | Olmsted |  | No Power
21 | Sweetbay/Yamaguchi |  | Sheared Planning to redrill
22 | End of Narcissa |  | Need to install generator
23 | Narcissa/Altamira |  | Sheared Installing surface pump
24 | Narcissa/Hunter | 6,517 | Generator Installed

## Slide 4: Budget/Spending/RPV Fast Track Loan
ACLAD 24/25 Budget
  2 New wells $250K
  Maintenance $130K ($200K?)
  Electric $36K ($120K Propane?)
  Reserve $100K
  Admin, consultants etc $52K
  Contingency $30
  Adopted Budget $598,000
RPV Fast Track Loan $1.6 M
  Altamira Cyn Planning
  Drainage Improvement
    Narcissa at PBRC
    Upper Narcissa to Ginger Root
    Narcissa at Cinnamon
    Cinnamon at Ride-to-Fly
    Vanderlip Dr
    Figtree
    Misc.
  System Improvement
    4 New Dewatering Wells
    Above ground drainage with flex joints
    System Optimization

## Slide 5: Budget/Spending/RPV Fast Track Loan Preliminary Recommendations Discussion
ACLAD 24/25 Budget
  2 New wells $250K
  Maintenance $130K ($200K?)
  Electric $36K ($120K Propane?)
  Reserve $100K
  Admin, consultants etc $52K
  Contingency $30
  Adopted Budget $598,000
  +$215,000
RPV Fast Track Loan $1.6 M Refuse most or all of loan
  Altamira Cyn Planning
  Drainage Improvement
    Narcissa at PBRC $40K (Retention tank and Trash Pump)
    Upper Narcissa to Ginger Root $10K (~12” HDPE Pipe from Narcissa)
    Narcissa at Cinnamon $30K (Fill and 12” Pipe at Cinn, 24” pipe Nar.)
    Cinnamon at Ride-to-Fly
    Vanderlip Dr $20K (Curbing on SW side to drain to Narcissa storm drain
    Figtree $25K (repair culvert and direct water flow thru cul de sac)
  System Improvement
    4 New Dewatering Wells
    Above ground drainage with flex joints $25K (install above ground pipe at WW13 to Cinnamon, Tootle to PVDS)
    System Optimization
    Solar and Batteries $ 10K – $40 K per well
RPV Winterization and DDW Plan, CC 10/1/24
  Drill 4-5 Deep De-watering Wells near ocean
  Grade, Fill, and line upper Altamira Canyon at fissures
  Fill fissures above Upper Cinnamon

## Slide 6: Solar
Working on design for Solar/Battery power
Full time well uses ~36 solar panels + $20K battery
May need to change pumps to DC
Only running the wells during the day does not require batteries
WW | Location | Priority | On % | Comments
1 | Narcissa/Ginger Root | A | 100 | Possible Solar
2 | Lower Narcissa | 0 |  | Sheared
3 | Figtree | B | 10 | Generator or SCE
4 | Lower Figtree | 0 |  | Sheared
6 | Clove Tree | B | 10 | Possible Solar
7 | Mid Narcissa | 0 |  | Sheared
8 | Mid Sweetbay | B |  | Possible Solar or Generator near lift station
9 | Beach School | A | 50 | Possible Solar
10 | Figtree Cul de sac | A | 50 | Generator or SCE
11 | Bean Field | A | 100 | Solar or SCE (no generator because of access)
12 | Upper Ginger Root | A | 100 | Generator
13 | King/Sweetbay | A | 100 | Generator, Possible solar
15 | Vanderlip/Narcissa | A | 100 | Generator or SCE
16 | Petak/Sweetbay | A | 100 | Generator or SCE
17 | Thyme | B | 10 | Generator near lift station
18 | Olmsted | A | 50 | Possible Solar
19 | Beach School | A | 50 | Possible Solar
20 | Olmsted | A | 50 | Possible Solar
21 | Sweetbay/Yamaguchi | B |  | Possible Solar
22 | End of Narcissa | B | 20 | Possible Solar
23 | Narcissa/Altamira | 0 |  | Sheared Installing surface pump
24 | Narcissa/Hunter | A | 100 | Generator or SCE